CURRENT IMPLEMENTATION NOTICE — October 2026: The original Streamlit deployment description in this PRD is superseded. BuildPay AI is now implemented as a Next.js/React web application with a FastAPI backend and PostgreSQL, deployed to Microsoft Azure.

BUILDPAY AI

Product Requirements Document

AI-Assisted Construction Payment & Work Approval Platform

| Document Control | Value |
| --- | --- |
| Version | 1.0 |
| Status | Product Requirements / Baseline |
| Date | 03 October 2026 |
| UI | Streamlit |
| AI Orchestration | CrewAI |
| LLM | Groq / openai/gpt-oss-120b |
| Deployment | GitHub + Streamlit Community Cloud |
| Authority | Human decision-makers |

Core principle: AI prepares, checks, calculates and flags; humans authorize.

# Table of Contents

1. Executive Summary	2

2. Product Vision	2

3. Problem Statement	3

4. Goals and Objectives	3

5. Scope		3

6. Users and Human Roles	4

7. AI Workforce	4

8. End-to-End Workflow	5

9. Functional Requirements	6

10. BOQ Management	7

11. Check Request Management	7

12. Document & Evidence Management	7

13. Work Execution & Measurement	8

14. Variation Management	8

15. IPC Management	8

16. Human-in-the-Loop Approval	9

17. Records, History & Audit Trail	9

18. UI/UX Requirements	10

19. Data Model	10

20. Agent & Tool Architecture	11

21. Non-Functional Requirements	11

22. Security & Governance	11

23. Reporting & Analytics	12

24. Deployment & Technical Stack	12

25. MVP Acceptance Criteria	12

26. Risks & Mitigations	13

27. Future Roadmap	13

28. Open Decisions	14

29. Glossary	14

# 1. Executive Summary

BuildPay AI is a multi-agent construction payment and work-approval platform for contractors, consultants, quantity surveyors, clients and authorized project personnel. It manages BOQ activities, Check Requests, supporting evidence, measurements, quantity variations, Interim Payment Certificates (IPCs), historical records and approvals. CrewAI orchestrates specialist agents; Groq provides the LLM; Streamlit provides the user interface.

The system is human-controlled. AI agents may extract information, perform deterministic calculations through tools, compare records, identify exceptions, prepare summaries and generate drafts. AI agents must never independently approve work, approve variations, approve IPCs or release payment.

# 2. Product Vision

Create a transparent, auditable and modular digital workforce that reduces manual construction-payment administration while preserving contractual authority and human accountability.

One controlled workflow from BOQ activity through Check Request, execution, variation and IPC.

Evidence-based AI review with explicit missing-evidence warnings.

Clear separation between AI recommendation and human authorization.

Historical traceability for quantities, approvals, variations and IPCs.

Simple role-based UI for Contractor, Consultant and Client.

Modular specialist agents maintained independently.

# 3. Problem Statement

Construction payment administration often relies on fragmented spreadsheets, email, scanned documents and manual reconciliation. This creates duplicate effort, weak traceability, late discovery of quantity overruns and difficulty proving how a certified amount was derived.

Link requests to exact BOQ activities.

Check quantities against original and approved revised quantities.

Maintain a formal Variation Register.

Generate IPC drafts only from eligible approved work.

Preserve AI findings and human decisions.

Surface missing evidence and duplicate/overrun risks before certification.

# 4. Goals and Objectives

| Goal | Success measure |
| --- | --- |
| Reduce administration | Less manual preparation/reconciliation for routine workflows. |
| Improve traceability | Every CR, variation and IPC links to BOQ, evidence and approvals. |
| Control overruns | Potential overrun is flagged before unsupported quantities enter an IPC. |
| Preserve authority | No AI-only approval or payment release. |
| Improve evidence completeness | Required documents are tracked by workflow stage. |
| Maintainability | Nine clearly bounded specialist agents. |

# 5. Scope

## 5.1 In Scope

Double-storey residential BOQ templates for 5 marla, 10 marla and 1 kanal.

Civil works only: mobilization, grey structure and finishing.

Contractor, Consultant and Client workspaces.

BOQ activity selection and quantity management.

Check Request creation, evidence upload and AI review.

Work execution and measurement capture.

Variation identification, summary, submission and approval.

Variation Register and historical reconciliation.

IPC generation, review and human approval.

Persistent records and audit trail.

## 5.2 Out of Scope for MVP

Automatic bank/payment execution.

AI contractual approval.

Full ERP/accounting integration.

Legal determination of claims/entitlement.

Automated site-sensor integration.

Certified engineering measurement without human verification.

OCR/vision certification replacing human review.

# 6. Users and Human Roles

| Role | Responsibilities |
| --- | --- |
| Contractor | Submit CRs, quantities, evidence, variation requests and executed quantities. |
| Consultant / Engineer | Technical review, measurement/evidence verification and recommendations. |
| Quantity Surveyor / Commercial Engineer | BOQ/rate reconciliation, variations, cumulative quantities and IPC review. |
| Client / Employer Representative | Human approval authority for work, variations and IPCs according to the project matrix. |
| Project Manager / Authorized Approver | Escalation and delegated approval of exceptional/high-value items. |

# 7. AI Workforce

| # | Agent | Responsibility |
| --- | --- | --- |
| 1 | BOQ & Activity Agent | Structures BOQ items, activities, units and original quantities. |
| 2 | Check Request Agent | Prepares and validates Check Requests against approved BOQ activities. |
| 3 | Document & Evidence Agent | Checks required documents and identifies missing/inconsistent evidence. |
| 4 | Measurement & Quantity Agent | Checks requested/executed and cumulative quantities. |
| 5 | Contract Compliance Agent | Checks supplied contract/specification requirements. |
| 6 | Variation in Quantity Agent | Identifies overruns, calculates additional quantities, summarizes justification and submits variations. |
| 7 | History & Duplicate Detection Agent | Compares current records with prior CRs, variations and IPCs. |
| 8 | IPC Preparation & Reconciliation Agent | Prepares IPC drafts from approved eligible work and reconciles values. |
| 9 | Review & Audit Agent | Consolidates findings and prepares human review/audit packages. |

# 8. End-to-End Workflow

Load/select the project BOQ and activity.

Contractor creates a Check Request linked to a BOQ item.

Contractor enters requested quantity and uploads evidence.

AI agents review BOQ linkage, evidence, quantity and compliance.

Review & Audit Agent prepares a consolidated brief.

Authorized human approves, returns or rejects the Check Request.

Approved work is executed.

Actual measurement and evidence are recorded.

AI compares actual/cumulative quantity with approved quantity.

If an overrun exists, a Variation Request is created.

Variation is reviewed and approved/returned/rejected by a human.

Only approved variations affect IPC eligibility.

IPC draft is generated and reconciled.

AI reviews IPC.

Authorized human approves or returns IPC.

Records remain available for history and audit.

Figure 1. End-to-end BuildPay AI workflow, including the human approval gates.

The following flowchart defines the controlled lifecycle. AI agents support analysis and preparation; human decision gates remain authoritative.

# 9. Functional Requirements

| ID | Requirement |
| --- | --- |
| FR-01 | Provide Contractor, Consultant and Client workspaces. |
| FR-02 | Select 5 marla, 10 marla or 1 kanal double-storey civil BOQ. |
| FR-03 | Create CR linked to an exact BOQ item. |
| FR-04 | Upload and associate supporting documents. |
| FR-05 | Run AI review and display current working agent. |
| FR-06 | Human can approve, return or reject CR. |
| FR-07 | Capture executed/current quantities and evidence. |
| FR-08 | Detect quantity overruns. |
| FR-09 | Create and maintain Variation Register records. |
| FR-10 | Only authorized humans approve variations. |
| FR-11 | Unapproved overruns cannot enter IPC eligibility. |
| FR-12 | Generate IPC draft from eligible approved work. |
| FR-13 | Human can approve/return IPC. |
| FR-14 | Retain CR, variation and IPC history. |
| FR-15 | Record material workflow actions in audit history. |

# 10. BOQ Management

MVP templates cover double-storey houses and only civil works: 5 marla, 10 marla and 1 kanal; mobilization, grey structure and finishing.

BOQ templates are illustrative planning/tender templates and must be validated against actual drawings, specifications, site conditions and applicable requirements before contractual use.

Item code

Section

Description

Unit

Original quantity

Unit rate

Amount

Notes

# 11. Check Request Management

A Check Request is the formal request to authorize/review a defined BOQ activity.

| Field | Purpose |
| --- | --- |
| CR number | Unique identifier |
| Project | Project association |
| BOQ item | Exact activity reference |
| Requested quantity | Proposed execution quantity |
| Unit | Measurement unit |
| Description | Execution context |
| Required documents | Evidence checklist |
| AI findings | Automated review |
| Human decision | Approve / Return / Reject |
| Approval metadata | Person, timestamp and comments |

# 12. Document & Evidence Management

Associate documents with project and relevant CR, variation or IPC.

Support PDF, DOCX, XLSX, CSV, TXT and Markdown in the MVP.

Track uploaded, reviewed, missing and rejected evidence.

Uploading a document does not mean it has been verified.

AI must explicitly state when evidence is unavailable or insufficient.

# 13. Work Execution & Measurement

After human approval, work proceeds according to the project's authorized workflow. Executed quantities are subsequently captured for measurement and IPC preparation.

Current quantity

Previously certified quantity

Cumulative quantity

Remaining approved quantity

Measurement evidence

Measurement date

Verifier

Comments

# 14. Variation Management

The Variation in Quantity Agent identifies quantity overruns, calculates the proposed additional quantity, summarizes justification and submits a variation for human approval. It cannot approve a variation.

| Field | Description |
| --- | --- |
| Variation number | Unique variation identifier |
| Linked CR | Originating Check Request |
| BOQ item | Affected activity |
| Original BOQ quantity | Original quantity |
| Previously approved variation | Prior approved addition |
| Current approved quantity | Original plus approved variations |
| Previously certified quantity | Cumulative certified quantity |
| Required cumulative quantity | Quantity needed based on measurement |
| Proposed additional quantity | New variation requested |
| Revised proposed quantity | Current approved quantity plus proposed addition |
| BOQ rate | Applicable rate |
| Estimated variation value | Additional quantity × rate |
| Justification | Reason for variation |
| Evidence | Supporting documents |
| Status | Draft / Submitted / Review / Approved / Returned / Rejected |
| Human approval | Approver, date and decision |

Control rule: an unapproved variation must not silently increase quantity eligible for an IPC.

# 15. IPC Management

IPC generation is restricted to work that has passed required approval and quantity controls.

Link IPC to approved CRs.

Include current, previous and cumulative quantities.

Use BOQ rates and approved variation rates where applicable.

Apply configured retention/deductions as deterministic calculations.

Show exceptions before human approval.

Link every IPC line to its BOQ item and source work/variation.

| Control | Rule |
| --- | --- |
| BOQ quantity | Cannot be exceeded without approved variation where contract rules require one. |
| Approved variation | Only approved variations increase eligible cumulative quantity. |
| Duplicate quantity | Prior certified quantity must be considered. |
| Evidence | Required evidence must be available. |
| Approval | Human approval required before final certification status. |

# 16. Human-in-the-Loop Approval

| Stage | AI role | Human role |
| --- | --- | --- |
| Check Request | Analyze and recommend | Approve / Return / Reject |
| Variation | Calculate and summarize | Approve / Return / Reject |
| IPC | Prepare and reconcile | Approve / Return |
| Payment release | No action | Authorized human/finance process |

AI recommendations must never be represented as human approvals.

# 17. Records, History & Audit Trail

Projects and BOQs

Check Requests

Documents and metadata

Measurements

Variations

IPC records and line items

AI findings

Human decisions

Approval timestamps

User identity/role

Audit events

SQLite is suitable for the prototype. Production should use managed persistent database and object storage.

# 18. UI/UX Requirements

Modern dashboard-style Streamlit UI.

Role navigation: Contractor, Consultant, Client, Records/Audit.

Clear status indicators.

Prominent current-agent indicator such as 'Measurement & Quantity Agent — Working'.

Progress indicators for multi-agent reviews.

Separate AI findings, human recommendations and final decisions.

Warnings for overruns and missing evidence.

Figure 2. Multi-agent architecture and tool-assisted orchestration.

Downloadable BOQ/IPC/report outputs.

Progressive, simple forms.

# 19. Data Model

| Entity | Key relationships |
| --- | --- |
| Project | Owns BOQs, users, CRs, variations and IPCs |
| BOQ | Belongs to project; contains BOQ items |
| BOQ Item | Referenced by CRs, measurements, variations and IPC lines |
| Check Request | References BOQ, documents, measurements and approvals |
| Document | Attached to CR, variation or IPC |
| Measurement | References BOQ item and CR/work |
| Variation | References BOQ item and originating CR; affects IPC eligibility when approved |
| IPC | Contains lines linked to approved work and variations |
| Approval | Human decision, role, timestamp and comments |
| Audit Event | Workflow/action history |

# 20. Agent & Tool Architecture

| Tool | Purpose |
| --- | --- |
| Document Reader | Extract text/data from uploaded documents. |
| BOQ Lookup | Retrieve exact BOQ activity, quantity, unit and rate. |
| Quantity/Payment Calculator | Perform deterministic quantity and amount arithmetic. |
| Required Document Checker | Compare required evidence with uploaded documents. |
| Historical Record Query | Retrieve prior CR, variation and IPC records. |
| Audit Recorder | Record workflow events and actions. |

Financial and quantity calculations should be deterministic tool outputs, not free-form LLM arithmetic.

# 21. Non-Functional Requirements

| Area | Requirement |
| --- | --- |
| Reliability | Agent errors must be visible and cannot silently create approval. |
| Performance | Show progress and current-agent status for long reviews. |
| Auditability | Material AI findings and all approvals are traceable. |
| Maintainability | Each agent is independently maintainable. |
| Extensibility | New rules/document types can be added without redesigning the UI. |
| Usability | Users understand status and next action. |
| Data integrity | Cumulative quantities and approved variations are deterministic. |

# 22. Security & Governance

Store API keys in Streamlit Secrets/environment configuration; never commit them.

Production users require authentication and role-based authorization.

Contractors cannot approve their own submissions.

AI has no payment-release credentials.

Uploaded documents have controlled access and retention.

Audit records should be append-oriented.

Production data should use managed persistent infrastructure.

# 23. Reporting & Analytics

Open CRs

Approved/returned/rejected CRs

Pending variations

Approved variation value

BOQ vs revised quantity

Current vs cumulative IPC quantities

IPC amounts by period

Exceptions

Missing evidence

Approval turnaround time

Project payment history

# 24. Deployment & Technical Stack

| Component | Technology |
| --- | --- |
| UI | Streamlit |
| Agent orchestration | CrewAI |
| LLM | Groq / openai/gpt-oss-120b |
| Document parsing | pypdf, python-docx, openpyxl |
| Prototype persistence | SQLite |
| Source control | GitHub |
| Deployment | Streamlit Community Cloud |
| Secrets | Streamlit Secrets |
| Production persistence | Managed PostgreSQL + object storage |

Dependencies should be pinned and tested against the selected Python runtime. The application should remain deployable through GitHub to Streamlit Cloud.

# 25. MVP Acceptance Criteria

Role workspaces function for Contractor, Consultant and Client.

BOQ templates are available for 5 marla, 10 marla and 1 kanal double-storey civil works.

Contractor can create CR against BOQ activity and upload evidence.

AI agents run visibly and show current working agent.

AI findings cover evidence, quantity, compliance and history.

Human can approve, return or reject CR.

Executed quantities can be recorded.

Overruns are detected before IPC eligibility.

Variation Register tracks proposed and approved variations.

Variation Agent calculates and summarizes proposed additional quantities.

Human can approve, return or reject variations.

Only approved variations affect IPC eligibility.

IPC can be generated from eligible approved work.

Human can approve or return IPC.

Previous records can be retrieved.

Audit history records key workflow events.

No AI action releases payment or provides final human approval.

# 26. Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| AI interpretation error | Structured fields, deterministic calculations, evidence references and human approval. |
| Hallucinated findings | Agents use document tools and report unavailable evidence. |
| Quantity duplication | History agent plus deterministic cumulative calculations. |
| Unauthorized approval | Role-based permissions and human-only approval actions. |
| Data loss in prototype | Move to managed DB/object storage for production. |
| Agent complexity | Nine clearly bounded agents with separate modules. |
| Contract differences | Externalize contract rules/configuration. |
| Scanned documents | Add OCR/vision later with human verification. |

# 27. Future Roadmap

| Phase | Focus |
| --- | --- |
| MVP | BOQ, CR, evidence, human approval, variation register, IPC, history. |
| Phase 2 | Managed PostgreSQL, object storage, authentication and permissions. |
| Phase 3 | OCR/vision for scanned documents, drawings and site photos. |
| Phase 4 | Contract-specific rules, change orders and advanced commercial reconciliation. |
| Phase 5 | ERP/accounting integrations and controlled finance workflows. |
| Phase 6 | Portfolio analytics and advanced exception detection. |

# 28. Open Decisions

Which contract forms/conditions govern compliance checks?

What documents are mandatory for each BOQ activity?

What approval thresholds apply to each human role?

Which retention, tax and deduction rules apply?

How are variations classified?

Which managed database/object storage provider will be used?

What authentication/SSO is required?

What document retention policy applies?

Which currencies and tax rules must be supported?

# 29. Glossary

| Term | Meaning |
| --- | --- |
| BOQ | Bill of Quantities. |
| CR | Check Request. |
| IPC | Interim Payment Certificate. |
| Variation | Approved change/addition to quantity or scope relative to the applicable baseline. |
| AI Agent | Specialized AI worker with a defined role and tools. |
| Human-in-the-loop | Workflow where designated humans retain decision authority. |
| Cumulative Quantity | Total quantity including previous and current quantities. |
| Approved Quantity | Quantity authorized under BOQ plus approved variations, subject to contract rules. |
| Evidence | Documents or records supporting a request, measurement, variation or IPC. |
| Audit Trail | Historical record of material system, AI and human actions/decisions. |

END OF PRODUCT REQUIREMENTS DOCUMENT

# Current Implementation & Deployment Update

Status: This section supersedes earlier Streamlit-specific deployment details and reflects the current BuildPay AI implementation and Azure deployment.

## 1. Current Application UI

BuildPay AI uses a modern Next.js 16 + React 19 frontend with TypeScript, Tailwind CSS, Radix UI components, Lucide icons, Framer Motion animations, and Recharts for data visualisation. The public experience starts at a dedicated landing page, followed by login and authenticated project-control workflows. The production UI is not a Streamlit application.

## 2. Backend & Data Layer

The backend is implemented with Python FastAPI and PostgreSQL database access. Authentication uses JWT-based access tokens. The application exposes REST APIs for projects, BOQ items, check requests, measurements, variations, IPC/payment workflows, documents, reports, AI findings, and audit events.

## 3. AI / Agent Framework Status

CrewAI is NOT used in the current BuildPay AI implementation. There is no CrewAI dependency or CrewAI-based orchestration in the repository. AI functionality follows the product principle: AI prepares, checks, calculates and flags; humans authorize. The current implementation uses the application's backend services and configured LLM integration rather than a CrewAI multi-agent runtime.

## 4. Azure Deployment Architecture

Microsoft Azure Container Apps hosts the frontend and backend as separate containerised services.

Azure Container Registry (ACR) stores the BuildPay AI frontend and backend Docker images.

Azure Database for PostgreSQL Flexible Server provides the production relational database.

Azure Container Apps Environment provides the shared managed container runtime and networking.

Azure Log Analytics is associated with the Container Apps environment for application/container logs.

The deployment uses HTTPS public ingress for the frontend and backend Container Apps.

## 5. Current Azure Resources

Resource group: buildpay-ai-rg

Container Apps environment: buildpay-ai-env

Container Registry: buildpayaiacr5908

Backend Container App: buildpay-backend

Frontend Container App: buildpay-frontend

PostgreSQL Flexible Server: buildpay-pg-3136

Database: buildpay

Azure region: Central India

## 6. Deployment Model

Both application tiers are built as Docker images. Images are pushed to Azure Container Registry and deployed to Azure Container Apps. The frontend is built with the production API base URL baked into the Next.js public environment configuration at build time. The backend receives database, JWT, LLM, and CORS configuration through Azure Container Apps environment variables and secret references rather than storing production secrets in the repository.

## 7. Demo & Role-Based Access

The application supports seeded demonstration accounts for Admin, Contractor, Consultant/QS, Client and Project Manager workflows. Role-based authorization remains enforced by the backend; the frontend login/demo-account UI is only a user experience layer.

## 8. Product Principle

BuildPay AI remains a human-in-the-loop construction project controls platform. AI assists with preparation, checking, calculations and anomaly/issue flagging, while authorized project participants retain responsibility for approvals, certifications and payments.

## 9. Superseded Streamlit Deployment

Any earlier section of this PRD that describes deploying BuildPay AI as a Streamlit app, including Streamlit-specific hosting, UI, startup commands or deployment instructions, should be treated as legacy project history and not as the current implementation. The authoritative deployment model is the Next.js + FastAPI + PostgreSQL stack described above, containerised with Docker and deployed on Azure Container Apps.